## Sheet1
Project Name | Project Manager | Start Date | End Date
Building a CI/CD Pipeline | Miriam Wanjohi | 2021-03-17 | 2021-06-09
Quarter | Month | Week | Task | Difficulty | Responsible | Status | % Complete | Comments
Project Introduction
Q1 | March | 2021-03-17 | Create a Project Plan | Low | Miriam W. | In Process
|  | 2021-03-24 | Excel Spreadsheet | Low | Miriam W. | In Process
|  | 2021-03-31 | Trello Board | Low | Miriam W. | In Process
Design Strucutre
| April | 2021-04-07 | Create Project Scaffolding | Intermediate | Miriam W. | Not Started
|  | 2021-04-14 | Set up Development Structure | Intermediate | Miriam W.
|  | 2021-04-21 | Test Code in Azure Cloud Shell | Intermediate | Miriam W.
|  | 2021-04-28 | Continuous Integration Setup Github Actions) | High | Miriam W.
Continuous Delivery
| May | 2021-05-05 | Set up Azure Pipeline | Low | Miriam W.
|  | 2021-05-12 | Create an AppService | Low | Miriam W.
|  | 2021-05-19 | Enable Github + Azure Pipelines | Intermediate | Miriam W.
|  | 2021-05-26 | Deploy App & Verify Prediction | High | Miriam W.
Demo & Submission
Q2 | June | 2021-06-02 | Update documentation and create a demo video | High | Miriam W.
|  | 2021-06-09 | Project Submssion | Low | Miriam W.
|  | Goals | Goals |  |  | Goals
|  | Ensure that the Project is submittted by April 18th | Verify that the Flask Prediction API retuns a valid JSON reposnse |  |  | Al tasks should be marked 'completed' once done
Github Repo has all the scaffolding files including the YAML config file
ReadMe is complete with all the necessary doumentations and screenshots
Demo Video is of good quality and clarity